## Procedures
APPENDIX 4.5 - BUDGET V ACTUAL TEMPLATE 2025
APPENDIX 4.5 - BUDGET V ACTUAL TEMPLATE 2025
BUDGET MONITORING REPORT (BMR)
A BMR is a financial report that shows actual income and expenditure for a certain period compared to the budget for the same period.
These reports are one of the most important tools to check that a project or projects are still on track, in financial terms. Any areas that are not on track can be identified, and action can be taken to put things right before any situation gets critical.
Key Points:
They should be prepared regularly throughout each project, normally once per month.
They should be reviewed straight away, once they are prepared.
It is good practice to organise a regular review meeting, including all team members, to discuss the financial position and decide on any actions that need to be taken.
Procedures
Once the monthly management accounts have been completed then the BMRs can be done.
Alternatively the BMRs could be part of the manamagent accounts process.
For the same currency budget see tab Budget v Actual for the following steps:
1. Establish the final agree budget and dates - it is important to ensure that the correct version is used as there are often many versions
Insert the start and end dates in the top part of the report
Each month end insert the month end date in the Report Date section (cell B5)
The % time remaining (cell S5) is based on those dates and is a formula to show the amount in percentage terms of time left in the project
2. Insert the correct budget figures in the yellow column
3. Input the actual expenditure amounts by line items in the blue section
Where a project crosses over two or more financial years you will need to always take account of the prior year's expenditure by bringing forward those numbers in a prior year column - see column D
3. Compare the budget v actual in the orange section
This is all formula driven to take the budget and minus the actual expenditure to show the balance left to spend or what is overspent
It also includes a total of the prior year expenditure as well
The final column is the balance left to spend or overspent in % terms
It is good to compare the overall total % left to spend with the time remaining % at the top of the sheet as in general they should be roughly the same percentage
However it is very important not to use this ridgidly as there could be very good explanations as to why the amount left might be larger or smaller than the time remaining %
E.g. If there was a large procurement done at the beginning of the project it could distort the % or if there is something large left to purchase
So this time remaining % is a guidance only
4. Where the donor budget is set in a currency other than the operating currency of the accounting system then the actual expenditure needs to be translated into the donor currency
See Tab Budget v Actual_Exchange for this where there is an extra section below to input the actual amounts in the operating currency and then this is translated into US$ by using the exchange rates at the end which come from the FX Rates tab

## Budget v Actual
Monthly Budget Report [Organisation & Project Name]
Start Date : | 2024-12-01 | [15 empty] | Project: | ABC
End Date : | 2025-11-30 | [15 empty] | Donor: | XYZ
Report Date: | 2025-09-30 | [14 empty] | % Time Remaining |  | 16.76%
| Account Codes | US$ | ACTUAL EXPENDITURE & INCOME US$ | [12 empty] | BUDGET v ACTUAL
Activities |  | TOTAL BUDGET | Prior Year | 2025-01-31 | 2025-02-28 | 2025-03-30 | 2025-04-27 | 2025-05-27 | 2025-06-24 | 2025-07-24 | 2025-08-21 | 2025-09-20 | 2025-10-26 | 2025-11-25 | Total Current Year | Total Prior Year & Current Year | Under / (Over) Spend US$ | Under / (Over) Spend %
Donor A |  | 124600 | 41500 | 2025-05-27: 41000; 2025-09-20: 42100 | 83100 | 124600 | 0 | 0%
Donor B |  | 78600 | 26200 | 2025-05-27: 26200; 2025-09-20: 26200 | 52400 | 78600 | 0 | 0%
Own Funds |  | 64800 | 64800 | [11 empty] | 0 | 64800 | 0 | 0%
In-kind |  | 27000 | 3000 | 2000 | 2000 | 2000 | 2000 | 3000 | 2000 | 2000 | 2000 | 2000 |  |  | 19000 | 22000 | 5000 | 22.73%
Total Income |  | 295000 | 135500 | 2000 | 2000 | 2000 | 2000 | 70200 | 2000 | 2000 | 2000 | 70300 | 0 | 0 | 154500 | 290000 | 5000 | 1.724%
Personnel | 2001 | 62500 | 5208 | 5208 | 5208 | 5208 | 5208 | 5208 | 5208 | 5208 | 5208 | 5208 |  |  | 46872 | 52080 | 10420 | 16.67%
Direct Programme Costs | 2002 | 104500 | 14000 | 3500 | 7000 | 13567 | 3787 | 17689 | 6789 | 9234 | 8232 | 2355 |  |  | 72153 | 86153 | 18347 | 17.56%
Distribution Costs | 2003 | 30200 | 2700 | 2718 | 2748 | 2567 | 2456 | 2897 | 2567 | 2431 | 2923 | 2223 |  |  | 23530 | 26230 | 3970 | 13.15%
Monitoring & Evaluation | 2004 | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4300 |  |  | 4300 | 4300 | 10700 | 71.33%
Equipment purchases | 2005 | 12000 | 6345 | 2025-01-31: 0; 2025-02-28: 2765; 2025-03-30: 0; 2025-04-27: 2890 | 5655 | 12000 | 0 | 0%
Travel costs | 2006 | 41900 | 1340 | 1340 | 1340 | 7840 | 1340 | 1340 | 6560 | 1340 | 1340 | 9340 |  |  | 31780 | 33120 | 8780 | 20.95%
Overheads | 2007 | 28900 | 2100 | 1980 | 3190 | 2780 | 2789 | 3245 | 3432 | 1876 | 2010 | 1453 |  |  | 22755 | 24855 | 4045 | 14%
Total Expenditure |  | 295000 | 31693 | 14746 | 22251 | 31962 | 18470 | 30379 | 24556 | 20089 | 19713 | 24879 | 0 | 0 | 207045 | 238738 | 56262 | 19.07%

## Budget v Actual_Exchange
Monthly Budget Report [Organisation & Project Name]
Start Date : | 2024-12-01 | [15 empty] | Project: | ABC
End Date : | 2025-11-30 | [15 empty] | Donor: | XYZ
Report Date: | 2025-09-30 | [14 empty] | % Time Remaining |  | 16.76%
| Account Codes | US$ | ACTUAL EXPENDITURE & INCOME US$ | [12 empty] | BUDGET v ACTUAL
Activities |  | TOTAL BUDGET | Prior Year | 2025-01-31 | 2025-02-28 | 2025-03-30 | 2025-04-27 | 2025-05-27 | 2025-06-24 | 2025-07-24 | 2025-08-21 | 2025-09-20 | 2025-10-26 | 2025-11-25 | Total Current Year | Total Prior Year & Current Year | Under / (Over) Spend US$ | Under / (Over) Spend %
Donor A |  | 124600 | 41500 | 2025-05-27: 41000; 2025-09-20: 42100 | 83100 | 124600 | 0 | 0%
Donor B |  | 78600 | 26200 | 2025-05-27: 26200; 2025-09-20: 26200 | 52400 | 78600 | 0 | 0%
Own Funds |  | 64800 | 64800 | [11 empty] | 0 | 64800 | 0 | 0%
In-kind |  | 27000 | 3000 | 2000 | 2000 | 2000 | 2000 | 3000 | 2000 | 2000 | 2000 | 2000 |  |  | 19000 | 22000 | 5000 | 22.73%
Total Income |  | 295000 | 135500 | 2000 | 2000 | 2000 | 2000 | 70200 | 2000 | 2000 | 2000 | 70300 | 0 | 0 | 154500 | 290000 | 5000 | 1.724%
Personnel | 2001 | 62500 | 5208 | 5208 | 5208 | 5208 | 5208 | 5208 | 5208 | 5208 | 5208 | 5208 | 0 | 0 | 46872 | 52080 | 10420 | 16.67%
Direct Programme Costs | 2002 | 104500 | 14000 | 3500 | 7000 | 13567 | 3787 | 17689 | 6789 | 9234 | 8232 | 2355 | 0 | 0 | 72153 | 86153 | 18347 | 17.56%
Distribution Costs | 2003 | 30200 | 2700 | 2718 | 2748 | 2567 | 2456 | 2897 | 2567 | 2431 | 2923 | 2223 | 0 | 0 | 23530 | 26230 | 3970 | 13.15%
Monitoring & Evaluation | 2004 | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4300 | 0 | 0 | 4300 | 4300 | 10700 | 71.33%
Equipment purchases | 2005 | 12000 | 6345 | 0 | 2765 | 0 | 2890 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5655 | 12000 | 0 | 0%
Travel costs | 2006 | 41900 | 1340 | 1340 | 1340 | 7840 | 1340 | 1340 | 6560 | 1340 | 1340 | 9340 | 0 | 0 | 31780 | 33120 | 8780 | 20.95%
Overheads | 2007 | 28900 | 2100 | 1980 | 3190 | 2780 | 2789 | 3245 | 3432 | 1876 | 2010 | 1453 | 0 | 0 | 22755 | 24855 | 4045 | 14%
Total Expenditure |  | 295000 | 31693 | 14746 | 22251 | 31962 | 18470 | 30379 | 24556 | 20089 | 19713 | 24879 | 0 | 0 | 207045 | 238738 | 56262 | 19.07%
|  | 4.5 | ACTUAL EXPENDITURE Local Currency | [12 empty] | BUDGET v ACTUAL
Activities | Account Codes | LOCAL BUDGET Currency | Prior Year | 2025-01-31 | 2025-02-28 | 2025-03-30 | 2025-04-27 | 2025-05-27 | 2025-06-24 | 2025-07-24 | 2025-08-21 | 2025-09-20 | 2025-10-26 | 2025-11-25 | Total Current Year | Total Prior Year & Current Year | Under / (Over) Spend US$ | Under / (Over) Spend %
Donor A |  | 560700 | 189240 | 0 | 0 | 0 | 0 | 156304.3 | 0 | 0 | 0 | 144036.73 |  |  | 300341.03 | 489581.03 | 71118.97 | 14.53%
Donor B |  | 353700 | 119472 | 0 | 0 | 0 | 0 | 99882.26 | 0 | 0 | 0 | 89638.06 |  |  | 189520.32 | 308992.32 | 44707.68 | 14.47%
Own Funds |  | 291600 | 295488 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 295488 | -3888 | -1.316%
In-kind |  | 121500 | 13680 | 8430 | 8247 | 7969 | 7712.8 | 11436.9 | 7425 | 7250.8 | 7049.6 | 6842.6 |  |  | 72363.7 | 86043.7 | 35456.3 | 41.21%
Total Icome |  | 1327500 | 617880 | 8430 | 8247 | 7969 | 7712.8 | 267623.46 | 7425 | 7250.8 | 7049.6 | 240517.39 | 0 | 0 | 562225.05 | 1180105.05 | 147394.95 | 12.49%
Personnel | 2001 | 281250 | 23748.48 | 21951.72 | 21475.188 | 20751.276 | 20084.1312 | 19854.4584 | 19334.7 | 18881.0832 | 18357.1584 | 17818.1304 | 0 | 0 | 178507.8456 | 202256.3256 | 78993.6744 | 28.09%
Direct Programme Costs | 2002 | 470250 | 63840 | 14752.5 | 28864.5 | 54057.7115 | 14604.1868 | 67435.7747 | 25204.1625 | 33476.9436 | 29016.1536 | 8057.1615 | 0 | 0 | 275469.0942 | 339309.0942 | 130940.9058 | 27.84%
Distribution Costs | 2003 | 135900 | 12312 | 11456.37 | 11331.378 | 10228.2115 | 9471.3184 | 11044.2331 | 9529.9875 | 8813.3474 | 10302.9904 | 7605.5499 | 0 | 0 | 89783.3862 | 102095.3862 | 33804.6138 | 24.87%
Monitoring & Evaluation | 2004 | 67500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14711.59 | 0 | 0 | 14711.59 | 14711.59 | 52788.41 | 78.21%
Equipment purchases | 2005 | 54000 | 28933.2 | 0 | 11401.4775 | 0 | 11144.996 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22546.4735 | 51479.6735 | 2520.3265 | 4.667%
Travel costs | 2006 | 188550 | 6110.4 | 5648.1 | 5525.49 | 31238.48 | 5167.576 | 5108.482 | 24354 | 4858.036 | 4723.232 | 31954.942 | 0 | 0 | 118578.338 | 124688.738 | 63861.262 | 33.87%
Overheads | 2007 | 130050 | 9576 | 8345.7 | 13153.965 | 11076.91 | 10755.4996 | 12370.9135 | 12741.3 | 6801.2504 | 7084.848 | 4971.1489 | 0 | 0 | 87301.5354 | 96877.5354 | 33172.4646 | 25.51%
Totals |  | 1327500 | 144520.08 | 62154.39 | 91751.9985 | 127352.589 | 71227.708 | 115813.8617 | 91164.15 | 72830.6606 | 69484.3824 | 85118.5227 | 0 | 0 | 786898.2629 | 931418.3429 | 396081.6571 | 29.84%
Exchange Rates |  |  | 4.56 | 4.215 | 4.1235 | 3.9845 | 3.8564 | 3.8123 | 3.7125 | 3.6254 | 3.5248 | 3.4213 |  | 0 | 3.8006

## Budget v Forecast
Monthly Budget Report [Organisation & Project Name]
Start Date : | 2024-12-01 | [15 empty] | Project: | ABC
End Date : | 2025-11-30 | [15 empty] | Donor: | XYZ
Report Date: | 2025-09-30 | [14 empty] | % Time Remaining |  | 16.76%
| Account Codes | US$ | ACTUAL V FORECAST EXPENDITURE & INCOME US$ | [12 empty] | BUDGET v FORECAST
|  |  | Actual | Actual | Actual | Actual | Actual | Actual | Actual | Actual | Actual | Actual | Forecast | Forecast |  | Total Prior Year & Current Year | Under / (Over) Spend US$ | Under / (Over) Spend %
Activities |  | TOTAL BUDGET | Prior Year | 2025-01-31 | 2025-02-28 | 2025-03-30 | 2025-04-27 | 2025-05-27 | 2025-06-24 | 2025-07-24 | 2025-08-21 | 2025-09-20 | 2025-10-26 | 2025-11-25 | Total Current Year
Donor A |  | 124600 | 41500 | 2025-05-27: 41000; 2025-09-20: 42100 | 83100 | 124600 | 0 | 0%
Donor B |  | 78600 | 26200 | 2025-05-27: 26200; 2025-09-20: 26200 | 52400 | 78600 | 0 | 0%
Own Funds |  | 64800 | 64800 | [11 empty] | 0 | 64800 | 0 | 0%
In-kind |  | 27000 | 3000 | 2000 | 2000 | 2000 | 2000 | 3000 | 2000 | 2000 | 2000 | 2000 | 2000 | 3000 | 24000 | 27000 | 0 | 0%
Total Income |  | 295000 | 135500 | 2000 | 2000 | 2000 | 2000 | 70200 | 2000 | 2000 | 2000 | 70300 | 2000 | 3000 | 159500 | 295000 | 0 | 0%
Personnel | 2001 | 62500 | 5208 | 5208 | 5208 | 5208 | 5208 | 5208 | 5208 | 5208 | 5208 | 5208 | 5208 | 5212 | 57292 | 62500 | 0 | 0%
Direct Programme Costs | 2002 | 104500 | 14000 | 3500 | 7000 | 13567 | 3787 | 17689 | 6789 | 9234 | 8232 | 2355 | 9345 | 8810 | 90308 | 104308 | 192 | 0.1837%
Distribution Costs | 2003 | 30200 | 2700 | 2718 | 2748 | 2567 | 2456 | 2897 | 2567 | 2431 | 2923 | 2223 | 2050 | 2400 | 27980 | 30680 | -480 | -1.589%
Monitoring & Evaluation | 2004 | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4300 |  | 10200 | 14500 | 14500 | 500 | 3.333%
Equipment purchases | 2005 | 12000 | 6345 | 0 | 2765 | 0 | 2890 | 0 | 0 | 0 | 0 | 0 |  |  | 5655 | 12000 | 0 | 0%
Travel costs | 2006 | 41900 | 1340 | 1340 | 1340 | 7840 | 1340 | 1340 | 6560 | 1340 | 1340 | 9340 | 4322 | 4122 | 40224 | 41564 | 336 | 0.8019%
Overheads | 2007 | 28900 | 2100 | 1980 | 3190 | 2780 | 2789 | 3245 | 3432 | 1876 | 2010 | 1453 | 2111 | 2324 | 27190 | 29290 | -390 | -1.349%
Total Expenditure |  | 295000 | 31693 | 14746 | 22251 | 31962 | 18470 | 30379 | 24556 | 20089 | 19713 | 24879 | 23036 | 33068 | 263149 | 294842 | 158 | 0.05356%

## Funding Grid
Funding Grid Example
Confirmed funding
Budget Item | Account Codes | TOTAL BUDGET | Donor A | Donor B | Own Funds | Own Funds | In-kind | Subtotal | Balance
Personnel | 2001-2010 | 62500 | 30000 | 22500 | 5000 |  | 5000 | 62500 | 0
Direct Programme Costs | 2020-2029 | 104500 | 54500 | 20000 | 25200 |  | 4800 | 104500 | 0
Distribution Costs | 2030-2039 | 30200 | 10300 | 5600 | 8800 |  | 5500 | 30200 | 0
Monitoring & Evaluation | 2040-2049 | 15000 |  | 12500 |  |  | 2500 | 15000 | 0
Equipment purchases | 2050-2059 | 12000 | 6000 |  | 6000 |  |  | 12000 | 0
Travel costs | 2060-2069 | 41900 | 12500 | 10700 | 13000 |  | 5700 | 41900 | 0
Overheads | 2070-2079 | 28900 | 11300 | 7300 | 6800 |  | 3500 | 28900 | 0
Totals |  | 295000 | 124600 | 78600 | 64800 | 0 | 27000 | 295000 | 0
|  |  | 42.24% | 26.64% | 21.97% |  | 9.153% | 100%

## FX Rates
Foreign Currency Exchange rates
Year 2025
Month End Spot Rates
Base Currency = LOCAL vs : | Stg£ | US$ | MONTH
2024-12-31 | 0.7375 | 4.56
2025-01-31 | 0.748 | 4.215 | 1
2025-02-28 | 0.7642 | 4.1235 | 1
2025-03-31 | 0.7931 | 3.9845 | 1
Qtr 1 avg | 0.7684 | 4.1077 | 3
2025-04-30 | 0.7936 | 3.8564 | 1
2025-05-30 | 0.7834 | 3.8123 | 1
2025-06-29 | 0.7921 | 3.7125 | 1
Qtr 2 avg | 0.7897 | 3.7937 | 3
2025-07-29 | 0.7883 | 3.6254 | 1
2025-08-28 | 0.8059 | 3.5248 | 1
2025-09-27 | 0.7977 | 3.4213 | 1
Qtr 3 avg | 0.7973 | 3.5238 | 3
2025-10-27 | 0.7848 | 3.2156 | 1
2025-11-26
2025-12-26
Qtr 4 avg | 0.7848 | 3.2156 | 1
YTD avg | 0.7851 | 3.7491 | 10
Formulas:
Base Currency = LOCAL vs : = +[Base Currency = LOCAL vs :, row above]+30
Note on D5: dmcmahon: Update this column when the new monthly rate is updated i.e. as each month passes
Note on B9: dmcmahon: This is the closing rate