MISSION FINANCE MANUAL

APPENDIX 7.3

DONOR PROPOSAL BUDGETING TOOL

GUIDELINES AND COMPLETION NOTES

CONTENTS

1	Overview of Budgeting Process	2

1.1	Aims and Objectives	2

1.2	Context – When to follow this process	2

1.3	Excel Spreadsheet Tool	2

2	Detailed Budgeting Process	2

3	Proposal Submission	5

4	Proposal Acceptance	6

4.1	Edmund Rice Development Project Funding Contract	6

5	Grant Management opening meeting	6

5.1	Attendees	6

5.2	Meeting topics	6

# Overview of Budgeting Process

## Aims and Objectives

The aim of this tool to provide a comprehensive budgeting process by doing the following:

- Standardize the budgeting process.

- Provide clarity around roles and responsibilities and timing of reviews.

- Incorporate Donor compliance review into the budgeting process.

- Ensure information is consolidated in one place.

- Provide consistent approach to the budgeting process.

## Context – When to follow this process

This is a process that could be followed for all proposals that are being completed.

It is not necessary to complete this for initial concept notes, however if there is any detail or calculations of a budget required it is recommended to use the template as it will provide the basis for the future proposals and eliminate any duplication.

## Excel Spreadsheet Tool

This document is accompanied by an excel spreadsheet which is the “Budget Template” that has been set up as a standard template to be used and should not be amended as a rule but can and should be reviewed on a regular basis to be amended as ideas arise from personnel for improving the process.

The tool has the following tabs in the workbook:

- Budget narrative

- Budget summary – In generic format

- Direct Programme costs (Activity workings)

- Personnel

- Equipment

- Travel

- Field and Country HO overhead calculations

- Visibility and M&E

# Detailed Budgeting Process

The person responsible for preparing the donor proposal should notify ERD/ERFA that they are setting up a proposal.

ERD/ERFA will send back the donor budget templates to be completed for the submission.

When they receive the donor templates they should add these into the Budget Template and link them to the “Budget Summary Generic” tab.

Then the local currency exchange rate should be updated. This only needs to be done once as all sheets are linked to the exchange rate cell C1in the Direct Programme Workings tab (defined as a Name “Exchange_Rate”)

Tabs should be completed in the following sequence as the “Budget Summary Generic” tab is linked to all the other tabs.

Direct Programme Costs (Activity Workings)

- It is recommended to start with the direct programme costs (activity workings) tab as these will more than likely provide or drive the key information to work out personnel (staffing), equipment and other support costs.

- Costs should be calculated in the currency they are sourced in and hence why there are two columns for currency – if you input into the [USD/local currency] the [€/USD] is automatically updated.

- Budgeting should be done on a “bottom up” basis – this means to start with the requirements for the programme as detailed as necessary, not aiming to achieve any target figure but working out the programme activities and needs which then achieve a final total amount.

- As low a level of detail should be done and then grouped for the donor reporting – the donor does not need to see all the levels of detail and if they do then they will audit against those lines, therefore it is preferable to only report to the donor at a high level to allow for flexibility. However internally this detail is necessary for budget monitoring and for the programme managers to code their costs when requesting orders.

- Account codes can be added as part of the final preparation once the programme is funded.

- The ‘notes’ section is particularly important. It explains how you have budget lines have been worked out and where the information was obtained from. This can really help when using budgets, or take account of changes in project plans or costs.

  - This is applicable to all tabs below.

Personnel

- Enter details of staff to be budgeted, including name, % allocated to the donor and pay level.

  - % allocated is generally for the support staff where they are allocated to donors based on the time it is estimated they will spend on that donor programme e.g. finance staff may be split across 4 donors 25% to each

- Any international staff should be input by function e.g. Advisor etc. and in general by person unless there will be many people performing the same role e.g. community development workers and so then enter one line for the function and input the number of those workers.

- National staff should be entered by person for most roles except for guards and drivers who should be entered as one line inputting the total number of them in the unit column.

  - It is recommended to break national staff into Direct Programme staff and Support Staff and to only report the totals of these sections to the donor as this will give flexibility in the actual spending of the budget i.e. if the donor sees line by line staff then you have to report against those lines.

- Enter the unit costs and

Travel

- Calculate the flights that will be required for this programme.

  - Where flights relate directly to a programme activity they can be input on the direct programme tab and not in this general travel section.

- If internal or regional flights are to be used for this programme work out how many and the cost of them.

- Obtain vehicle fuel and repair costs etc. to complete this tab.

  - Always include insurance and other transport costs like taxis or public transport when used.

Equipment

- Enter details of equipment to be purchased ensuring to capture all anticipated expenditure particularly new computer equipment and office equipment.

- Obtain the costs of equipment ensuring to include all customs and tax related costs as well as transport costs of equipment in the budget (costs that are directly related to the purchase of something should be added to that budget line not the general transport line – same applies for customs)

- Enter the location equipment will be located at (especially applicable for computer equipment).

Visibility & M&E

- Visibility includes costs like t-shirts, banners, flags or plaques, basically any costs where the logo of the [province / region / organisation] and or the donor are being put.

  - Note though that if there are budgets set for this then it must be ensured that the donor logo is put on the items as well as those of the [province / region / organisation].

- A detailed budget for monitoring and evaluation (M&E) should also be included on this tab and make sure to include all visitors anticipated but only as long as they will be reviewing the programme under this donor.

  - These are usually costs for travel for personnel performing the evaluations.

Overhead costs

- These are the standard costs for office rent, telephone bills, utility bills, stationery etc.

- Figures should be based on historical information for the [province / region / organisation].

Budget narrative

A budget narrative is sometimes required by donors, however even if it is not mandatory it is a very useful high level summary in a written format of the budget and it is also a helpful document to cross check from the financial budget to the programme narrative written to the donor and therefore it is advised to always complete this for all budgets regardless of whether the donor requires it or not.

The importance of this tab cannot be emphasized enough

- It provides a summary of the costs in a narrative format

- It can be used to provide information pertaining to ownership of assets at the end of the programme

- Donors are less likely to query costs if this is written efficiently and clearly

- Therefore they are more likely to approve the proposal and budget quicker and this can only improve donor relations by proving the professionalism of the organisation.

  - You are only as good as your last proposal

- It can also help particularly where personnel have changed over and new personnel are taking over existing programmes, the same way the notes in each tab can assist for tracking more details of the activities.

Once this provisional budget has been completed, it should be reviewed with ERD/ERFA.

As the budget is now finalised for the proposal as a provisional budget it should then be sent from [………………….] for a final review to the following:

# Proposal Submission

The [CEO/Province Leader/Regional Leader/District Leader] will send the proposal (Narrative, Budget and Budget Narrative) to ERD/ERFA.

ERD/ERFA will review the proposal and either send back queries to be acted on or approve the proposal by e-mail to [CEO/Province Leader/Regional Leader/District Leader] who will then revert with all queries answered and the proposal is then finalised.

When the proposal is being submitted to the donor by ERD / ERFA, they will do the following:

- Delete any reference to “Drafts” of the proposal

- Name the documents to be submitted consistently and delete any version controls i.e. put final at the end of the name of the documents.

# Proposal Acceptance

Once the proposal is approved by the donor, the contract / agreement from the donor ERD / ERFA will be signed and they will let the [CEO/Province Leader/Regional Leader/District Leader].

- Programmes cannot commence until the grant agreement has been received signed by the donor unless there is a signed received Pre-Agreement Letter (PAL) from the donor.

## Edmund Rice Development Project Funding Contract

ERD/ERFA will prepare a Project Funding Contract which is the formal agreement between themselves and the [Province /Regional /Organisation].

A signed copy of the contract will be scanned to the [CEO/Province Leader/Regional Leader/District Leader] who should review the contract for the following:

- Correct start and end dates

- Correct amounts either in total or by category

- Acceptable reporting deadlines

- Conditions of funding releases e.g. tranches of cash only sent on receipt of reports

# Grant Management opening meeting

The [CEO/Province Leader/Regional Leader/District Leader] should arrange a grant opening meeting, the purpose of which is, to ensure that all teams are aware of the programme and their roles and responsibilities for the course of the programme.

## Attendees

Examples below to be changed per Province / Region / Organisation

- Coordinator

- Project Manager

- Financial Accountant

## Meeting topics

- Programme outline and timelines

  - The [………..]  should give a brief outline of the activities and timelines

- Finance issues

  - The person in charge of the finances will issue the final budget by account code as it will be reported monthly.

  - Finance need to ensure that everyone is aware of the variance rules governing the budget i.e. how much can be overspent within the budget categories.

- HR requirements

  - Identify any recruitment needs and agree a process and timeframe to hire new personnel etc.

- Logistics planning

  - Vehicle purchases or leases

  - Major procurements to be planned

- Donor Compliance

  - Tax issues – some donors will not allow taxes as an eligible cost unless the agency can prove that they are not entitled to claim back tax or have applied and being rejected

  - Source origin issues with the donor?

  - Timesheet requirements by the donor?

  - Donor reporting timetable

- Next Meeting dates

  - Agree how often meetings should be held to manage this programme and who should attend

[GLOBAL TEMPLATE] to be replaced with Province/Region/Organisation name e.g. ERI or Africa Province and where [province/region/organisation] is mentioned in further chapters delete as appropriate