At the beginning of a new project, it is recommended that the project team and finance officer meet to review the project agreement/contract, proposal and budget. It will be important to note key compliance and reporting requirements and plan appropriate activities, meetings and documentation to meet these:

  - Agreement ‘start’ and ‘end’ dates? (Expenditure must only be within these dates)

  - Agreement budget – is it the same as the proposal budget?

  - What is the allowable budget variance?

  - What are the rules & regulations for obtaining a No Cost Extension (NCE)?

  - Is there Co-funding (other contributions – cash or donations in kind (DIK))? What are their rules?

  - What are the Specific Donor Reporting Requirements and how often is reporting? Keep in mind the following for financial reporting - forex, deadlines, supporting documentation and record keeping 7 years, etc

  - Audit – what is the donor threshold for an audit? Will your project require an audit?

  - Results Framework – ensure ‘means of verification’ reports are filed monthly

  - M & E – what are the specific plans for M & E and what records and statistics are required?

Donor Compliance is a part of everyone’s job and responsibility!

Donor Compliance checklist – several checks required throughout the project period

- No expenditure before start date or after end date of donor contract dates

- Valid Staff Contracts: for all staff specified in the proposal budget and report

- HR: staff files, salary scales, timesheets (donors), leave records, all on file.

- International Travel: actual costs align to planned costs and flight tickets on file

- Allocations of admin/support costs to donors: are documented and ‘fair’ and close to actual

- Procurement plan devised and all equipment and stock were bought timely and in line with MFM procurement guidelines.

- Assets & Stock are safeguarded and movement of all items are tracked and on file including physical asset and stock checks throughout the year – signed off.

- Donations in kind – donation certificates detailing items, quantities & value on file.

- Finance/Budgeting – all coding of expenditure is carried out and assigned to donor budget lines correctly

- Beneficiary distributions – there is a system in place for documenting and recording all distributions/trainings/workshops for audit trail to evidence the activity.

Donor Reporting Essentials Summary

- Use the donor reporting format and preserve the formulae

- Ensure the Narrative Report, Financial Report and accounting system match such that quantities and figures all reconcile.

- Ensure all expenditure figures reported are backed up with an expenditure summary report from the accounting system and that all financial payment transactions are adequately documented and filed for audit purposes.

- Donor Reports must be against the original donor approved budget and one cannot change the budget without formal approval from the donor

- Ensure that all co-funding in cash and/or DIK is reported as part of the final report.

- You must gather data and report on both foreign exchange losses and gains in line with donor requests.

- Clearly and concisely explain and justify variances in the donor report as required where the budget line exceeds the allowable donor variance.